## Sheet1
Use Case Point Estimation Worksheet
Unadjusted Actor Weighting Table
Actor Type | Description | Weighting Factor | Number | Result
Simple | External System with well-defined API | 1 |  | 0
Average | External System using a protocol-based interface, e.g., HTTP, TCT/IP, or a database | 2 |  | 0
Complex | Human | 3 |  | 0
Unadjusted Actor Weight Total (UAW) |  |  |  | 0
Unadjusted Use Case Weighting Table
Use Case Type | Description | Weighting Factor | Number | Result
Simple | 1 – 3 transactions | 5 |  | 0
Average | 4 – 7 transactions | 10 |  | 0
Complex | > 7 transactions | 15 |  | 0
Unadjusted Use Case Weight Total (UUCW) |  |  |  | 0
Unadjusted Use Case Points (UUCP) = UAW + UUCW |  | 0
Technical Complexity Factors
Factor Number | Description | Weight | Assigned Value (0 – 5) | Weighted Value | Notes
T1 | Distributed system | 2 |  | 0
T2 | Response time or throughput performance objectives | 1 |  | 0
T3 | End-user online efficiency | 1 |  | 0
T4 | Complex internal processing | 1 |  | 0
T5 | Reusability of code | 1 |  | 0
T6 | Easy to install | 0.5 |  | 0
T7 | Ease of use | 0.5 |  | 0
T8 | Portability | 2 |  | 0
T9 | Ease of change | 1 |  | 0
T10 | Concurrency | 1 |  | 0
T11 | Special security objectives included | 1 |  | 0
T12 | Direct access for third parties | 1 |  | 0
T13 | Special User training required | 1 |  | 0
Technical Factor Value (TFactor) |  |  |  | 0
Technical Complexity Factor (TCF) = 0.6 + (0.01 * TFactor) |  | 0.6
Environmental Factors
Factor Number | Description | Weight | Assigned Value (0 – 5) | Weighted Value | Notes | PHM Counts
E1 | Familiarity with system development process being used | 1.5 |  | 0 |  | 1
E2 | Application experience | 0.5 |  | 0 |  | 1
E3 | Object-oriented experience | 1 |  | 0 |  | 1
E4 | Lead analyst capability | 0.5 |  | 0 |  | 1
E5 | Motivation | 1 |  | 0 |  | 1
E6 | Requirements stability | 2 |  | 0 |  | 1
E7 | Part time staff | -1 |  | 0 |  | 0
E8 | Difficulty of programming language | -1 |  | 0 |  | 0
Environmental Factor Value (EFactor) |  |  |  | 0 |  | 6
Environmental Factor (EF) = 1.4 + (-0.03 * EFactor) |  | 1.4
Adjusted Use Case Points (UCP) = UUCP * TCF * EF |  | 0
Person Hours Mulitiplier (PHM) |  | 0 | * A value of 0 means too risky to proceed
Effort in Person Hours = UCP * PHM |  | 0
| Yong Tan, U of Washington | http://faculty.washington.edu/ytan/is460/UseCasePoints.xls